## sprint_planning
Feature | Epic | User Stories | Ready to be planned | planned sprint | Estimation | Assignee
Create account | as a user i want to create account so that i can place orders | as a user i want to record my data once at sign-up so that i don`t want to enter my data again | YES | 1 | 40 hrs | Mahmoud
Create account | as a user i want to create account so that i can place orders | as a user i want to sign up easly so that i will sign by google or facebook | YES | 1 | 40 hrs | mohamed
view Restaurants | as a user i want to see all restaurants so that i want to order | as a user i want to see all nearby restaurants so that i want to order | YES | 2 | 80 hrs | Mahmoud , mohamed
view Restaurants | as a user i want to see all restaurants so that i want to order | as a user i want to see restaurant categorized by cusine so that i want to order easly | YES | 2 | 20 hrs | Mahmoud
Search restaurants | as a user i want to search restaurants so that i find the suitable restaurant | as a user i want to search with filters so that i find the most suitable food | NO | - | - | -
View Menu | as a user i want to view menu of the restaurant in its page so that i can choose my order | as a user i want to see the detailed meny when i open the restaurant page so that i choose my order easly | YES | 3 | 100 hrs | Mahmoud , mohamed

## sprint_back-log
Feature | Epic | User Stories
Create account | as a user i want to create account so that i can place orders | as a user i want to record my data once at sign-up so that i don`t want to enter my data again
Create account | as a user i want to create account so that i can place orders | as a user i want to sign up easly so that i will sign by google or facebook
view Restaurants | as a user i want to see all restaurants so that i want to order | as a user i want to see all nearby restaurants so that i want to order
view Restaurants | as a user i want to see all restaurants so that i want to order | as a user i want to see restaurant categorized by cusine so that i want to order easly
Search restaurants | as a user i want to search restaurants so that i find the suitable restaurant | as a user i want to search with filters so that i find the most suitable food
View Menu | as a user i want to view menu of the restaurant in its page so that i can choose my order | as a user i want to see the detailed meny when i open the restaurant page so that i choose my order easly